Program:  Sickle Cell Disease (SCD) Radio Awareness Raising and Sensitisation Campaign

Sponsor: Sickle Cell Support Society of Nigeria (SCSSN) - Pfizer Specialties Ltd

Locations: Selected Cities in the Six Geo-Political Zones of Nigeria

Duration: One Month of Radio spots, Three months of live programs

Dates: May 2026 - September 2026

The Radio Awareness Raising and Sensitisation Campaign project to encourage New Born Screening & Clinical Care Follow-up for Sickle Cell Disease (SCD) was initiated with key objectives to improve awareness, encourage more families to participate in newborn screening and ensure babies who test positive are brought back for follow-up clinical care. Radio stations were carefully selected for all demography and multiple touch points to cover specific areas in the six geopolitical zones across Nigeria.

1.0  Program Design

Produce radio jingles on SCD newborn screening and Follow-up care, focus radio campaign in selected radio stations across the six geopolitical zones of Nigeria. Radio presenters and guest experts trained to ensure message consistency. Point of care test kits distributed through coordinators of the six zones to encourage engagement. The combination of radio jingles with interactive phone-in programmes will measure program impact.

2.0  Campaign Metrics

| Zone | No. of Radio Stations (Target: 12) | Radio Spots (Target: 360) | Remarks |  | Live Programs (Target: 18) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| South South | 3 | 100 |  |  | 9 |  |
| North East | 2 | 93 | includes Hausa, Kanuri, Pidgin English |  | 6 | including in Hausa and Kanuri |
| North West | 4 | 63 |  |  | 7 | including in Hausa |
| South West | 3 | 60 | includes Yoruba |  | 9 | including in Yoruba |
| South East | 5 | 60 | includes Igbo |  | 10 |  |
| North Central | 4 | 82 |  |  | 11 |  |
| TOTAL | 21 | 458 |  |  | 52 |  |

3.0  Interventions

- Product: FAQs sheet on SCD care and on Newborn screening  for training radio presenters.

- Training:  Organise 3 training sessions for radio presenters and program guests

  - May 21, 2026:  39 trainees from 15 radio stations; faculty of 7 resource persons including 3 SCSSN zonal coordinators (SW,SS,NW)

  - June 1, 2026:   42 Trainees from 19 radio stations; faculty of 2 resource persons

  - Aug 13, 2026: 23 Trainees from 14 stations; faculty of 3 SCSSN coordinators (SW SS, NW); CESRTA team; 3 Warriors

- Multi-lingual jingles and live programs: Ensure cultural relevance through translations into dominant regional 		languages of pidgin-English, Hausa, Igbo, Kanuri, and Yoruba for more extensive local reach

- Live Programs: Used more prime time general interest programs than special health programs for greater reach.

4.0. Impact and Lessons

Qualitative feedback in the testimonials indicate that the training and live programs achieved the objectives of building media capacity, improving SCD awareness programming content, increasing listener knowledge through audience engagement and promoting positive attitude towards SCD warriors.

4.1  	Audience Lessons:

- Greater coverage of SCD prevention and management strategies

- More radio programs in local languages with more narratives from SCD warriors to reach under-served communities

- More discussions on family support and caregiving

4.2  	Broadcasters learned:

- Need for health information to be accurate and evidence-based

- That effective health communication requires simple and relatable language

- Audience engagement improves programme quality and impact

4.3	Challenges:

- Achieving satisfactory message saturation and measurable behavioral change with limited program duration and funding

- Securing guests and managing unexpected live program changes

- Simplifying medical information without losing accuracy, especially in the local languages

5.0	Conclusion and recommendation

The Radio Awareness Raising and Sensitisation Campaign to Encourage New Born Screening & Clinical Care Follow-up for Sickle Cell Disease warriors was successfully carried out in more radio stations and with more live programs than originally planned, which partially mitigated the challenge of execution, the guest pool was expanded, pre-recorded programs were utilised in a few instances while the factsheet enabled more standardised messaging.

Collective feedback demonstrates that radio remains a powerful tool for SCD awareness especially in under-served communities. The training equipped journalists with the knowledge and skills needed to produce impactful content, while listener responses confirmed a strong need for sustained public education on newborn screening, genotype testing, stigma reduction, and support for Sickle Cell Disease warriors.

Recommendations include:

- Continued investment in media training and public awareness programming

- Utilise feedback to improve program design features for a full national campaign

- Develop a system for sustaining the campaign after this  initial (pilot) funding

6.0  Campaign Summary

| Region | Cities | Radio Stations | Jingles Dates 2026 | Phone-in Dates 2026 | Remarks/ Results | Link |
| --- | --- | --- | --- | --- | --- | --- |
| South South | Uyo | Inspiration FM, Uyo | 23 May -21 Jun | 28 May 15 Jun 10 Jul 4 Sep 11 Sep | 90 spots | https://drive.google.com/file/d/1RttPyYr-YXkAx-9VgViMLcnHEgCI0lva/view?usp=drive_link https://drive.google.com/file/d/14xon2plfsAhKL0ISL_g1x8bc4gHk1Drp/view?usp=drive_link https://drive.google.com/file/d/1SS6TPrpnZCpRAs6HQL2yTGrbssXCXrFg/view?usp=drive_link https://drive.google.com/file/d/1gKRf0Rj9d2efjjrwNeKdtdocbOm5crqf/view?usp=drive_link https://drive.google.com/file/d/1ZnbllKfTDvAAETw-20mn58Kw3EJiBAl0/view?usp=drive_link |
|  | Uyo | Comfort FM, Uyo |  | 19 Jun |  |  |
|  | Calabar | HIT FM |  | 18 Jun 15 Jul 29 Jul | 10 Spots | https://drive.google.com/file/d/1itB41bEfXRXo2JG1lDDTLXJkfErWI_9w/view?usp=drive_link https://drive.google.com/file/d/1bi4ICu2-AU9qZL2rCJmIaXWeik-EciDO/view?usp=drive_link |
| North East | Maiduguri | Peace FM, | 31 May -30 Jun | 9 Jun 13 Jun 15 Jun 17 Jun 15 Jul | 93 Spots English, Kanuri & Hausa live programs | https://drive.google.com/file/d/1J9xaMkQ8I8STnoBU1z3dbkaiFUdopLjb/view?usp=drive_link https://drive.google.com/file/d/1MEIaJcmWJNa6QKoXD8FZHLJjmHcl_uZ2/view?usp=drive_link https://drive.google.com/file/d/193i30Pwb03PYhp5GUvPeEDsaieg8Q0UJ/view?usp=drive_link https://drive.google.com/file/d/1uYuPtNzdhxEmJXCK9zKe1XFotKFE9Izr/view?usp=drive_link https://drive.google.com/file/d/1rlrYXSqbegb1Qu8Uk_gKGHR3HtacRHAU/view?usp=drive_link |
|  | Yola | Usaku FM |  | 13 Jul |  |  |
| North West | Kebbi | Nagari FM, Kebbi | 9Jun-18Jun | 18 Jun | 30 Spots |  |
|  | Kaduna | Nagarta Radio | 7Jun-6Jul | 17Jun (Hausa) 22 Jul |  | https://drive.google.com/file/d/1SggXMxaLZDhahFBebWcGeeNREmm6R4Ze/view?usp=drive_link https://drive.google.com/file/d/1YkyJLrJ97uRYIDE6GnVFMxaMGukXiBxS/view?usp=drive_link |
|  | Zaria | ABU Radio | 7Jun-29 Jul | 11 Jun |  | https://drive.google.com/file/d/1wGPPmRUEyvj3vGBiQ1KoiE5GU2By8XU7/view?usp=drive_link https://drive.google.com/file/d/1LQhmwIsSAiTm9X16hmkcgJlol5lccn-p/view?usp=drive_link |
|  |  | Queen FM | 7Jun–10 Jul | 10Jun (Hausa) 19 Jun 21 Jul | 33 Spots | https://drive.google.com/file/d/1X02cnlv3otVmtbihJpAq3MrzKxSL7s8X/view?usp=drive_link https://drive.google.com/file/d/1puZKgGFHH6uKj3yD2LPZXi6TeeD6PyPu/view?usp=drive_link |
| South West | Ife | Crown FM, Ife | 18Jun-18 Jul | 19 Jun 3 Sep 10 Sep | 30 spots including Yoruba |  |
|  | Ilesha | Diamond Radio, Ilesha | 18Jun-17 Jul | 11 Jul 31 Jul | 30 spots including Yoruba |  |
|  | Lagos | Radio Lagos |  | 23 Jul 30 Jul 06 Aug 13 Aug | Yoruba | https://drive.google.com/file/d/1dRQ2tp-Flue4lDgPPqJGKnXKtmVJs7Te/view?usp=drive_link https://drive.google.com/file/d/1_pAA8dJdjKbp3LeG-RyzLPyoLx-OfP8C/view?usp=drive_link https://drive.google.com/file/d/1YncTAfwLezogzfTpygEDslDughof9A3I/view?usp=drive_link https://drive.google.com/file/d/1JKUSaJayxC4iZ2Wk8tvRFd3TrxCC5Yh3/view?usp=drive_link |
| South East | Onitsha | Sapienta FM | 19 Jun -15 Jul 2026 (Igbo) | 19 Jun (Igbo) | 60 spots |  |
|  | Ora Ifite | Blaze FM | 13Jun-27Jun | 19 Jun 16 Jul |  |  |
|  | Ora Ifite | Ijele FM | 13Jun-29 Jun (Igbo) | 17Jul (Igbo) |  | https://drive.google.com/file/d/1CnnkcQ6wnCytaNUMIj19Hlq8zm_TBnJ0/view?usp=drive_link |
|  | Enugu | Dream FM |  | 18 Jun 23 Jul 30 Jul 1 Sep 8 Sep |  | https://drive.google.com/file/d/1lQLn7HDbStrbzoe77xZVSePrckqJ2XJQ/view?usp=drive_link |
|  | Nnewi | Authority FM |  | 21 Jun |  |  |
| North Central | Abuja | Kapital FM (FRCN) | 2Jul-31Jul extended to 11 Aug 2026 | 20 Jul 22 Jul 28 Jul 31Aug (rec) 7Aug (rec) 14Aug(rec) | 60 spots 22 added | https://drive.google.com/file/d/1pChh8AibRu3NPU-hbQjUR2ZYXqyBOKES/view?usp=drive_link https://drive.google.com/file/d/1KeE1oizJdzs7ZqqdJ4wFHnh_aV7sb68z/view?usp=drive_link |
|  | Abuja | Kids FM |  | 21 Jul |  |  |
|  | Abuja | Municipal FM |  | 15 Jul |  |  |
|  | Abuja | Global TV |  | 23 Aug |  | https://youtu.be/jtg_bCvxx-Y?si=nYjvJt4ldu8sGf_S |
|  | Jos | PRTV, Jos |  | 3 Jun 21 Jul |  | https://www.youtube.com/live/BU_O4DJ1Q-o?si=aOkl5DP6_GLIe50k |

7.0	Resources

| - SCD & Newborn Screening FAQ |  |
| --- | --- |
| - Testimonials |  |

8.0 	PICTURE GALLERY

FRCN Kapital FM, Abuja FCT

Inspiration FM, Uyo, Akwa Ibom State

Inspiration FM - Uyo, AKwa Ibom State

Peace FM, Maiduguri, Borno State  - KANURI language  Live Porgram